## W & G
JIGAWA STATE SMALL TOWNS WATER SUPLLY AND SANITATION AGENCY (STOWA)
ANNUAL PROCUREMENT PLAN
PROCUREMENT PLAN FOR WORKS AND GOODS CONTRACTS
| MINISTRY/ AGENCY: | STOWA
| BUDGET YEAR: | 2023
| PROJECT PARTICULARS |  |  |  | BASIC DATA |  |  | PROJECT PREPARATION |  |  |  | BIDDING PERIOD |  | BID EVALUATION & AWARD |  |  | CONTRACT MANAGEMENT & ADMINISTRATION |  |  |  | ANY OTHER REMARKS
| Project Description | Economic Code | Package No./File No. | Lot No. | Revised Threshold/ Budgeted Amount (Naira) | Estimated Amount in Naira | Procurement Method | Preparation & Submission of documents by MDAs | Post Review/ Vetting | Advert for Pre - Qualification | Pre-Qualification | Bid Invitation | Bid receipt and opening | Bid Evaluation& Report | Consideration of TEC Recommendation | Due Process Certificate of No Objection | Contract Approval & Offer | Contract Signing | Delivery/handover and acceptance | Final Payment
Date: Plan | i. Rehabilitation of existing small towns water supply schemes | 020404/02 | STOWA/2023/CP/REHAB./1 | NA | 400million | 100 million | Selective method | 31/01/2023-3/02/2023 | 6/02/2023-13/02/2023 | NA | 13/02/2023-17/2/2023 | 20/2/2023-27/2/2023 | 20/2/2023-27/2/2023 | 27/2/2023-6/03/2023 | 6/3/2023-8/3/2023 | 8/3/2023-15/3/2023 | 15/3/2023-22/3/2023 | 22/3/2023-23/3/2023 | 23/3/2023-13/4/2023 | 13/4/2023-20/4/2023 | First Quarter
Date: Actual
Cost :Plan | [18 empty] | 50000
Cost: Actual
Responsibility | [7 empty] | Procurement Officer | D.G Due Process |  | Procurement Officer | Procurement Officer | Procurement Officer | Procurement Officer | Ag. MD | D.G. Due Procrss | Executive Governor | Ag. MD | Director Technical Support | Commissioner of Finance
Date: Plan | ii. Construction of 30No. New conventional solar water schemes across the 7 zones | 020408/02 | STOWA/2022/CP/2 | NA | 224.24 million | 80 million | sellective method | 31/01/2023-3/02/2023 | 6/02/2023-13/02/2023 | NA | 13/02/2023-17/2/2023 | 20/2/2023-27/2/2023 | 20/2/2023-27/2/2023 | 27/2/2023-6/03/2023 | 6/3/2023-8/3/2023 | 8/3/2023-15/3/2023 | 15/3/2023-22/3/2023 | 22/3/2023-23/3/2023 | 23/3/2023-13/4/2023 | 28//3/2023-31/3/2023 | First Quarter
Date: Actual
Cost :Plan | [7 empty] | 20000 |  |  | 30000 |  |  | 120000 | 30000 |  |  |  | 50000
Cost: Actual
Responsibility | [7 empty] | Procurement Officer | D.G Due Process |  | Procurement Officer | Procurement Officer | Procurement Officer | Procurement Officer | Ag. MD | D.G. Due Procrss | Executive Governor | Ag. MD | Director Technical Support | Commissioner of Finance
Date: Plan | iii.Conversion and upgrading of 36No. motorized water supply scheme to solar powered water supply schemes | 020408/02 | STOWA/2022/PROJ/CP/6 | NA | 500 Million | 200 Million | selective competitive Method | 31/01/2023-3/02/2023 | 6/02/2023-13/02/2023 | NA | 13/02/2023-17/2/2023 | 20/2/2023-27/2/2023 | 20/2/2023-27/2/2023 | 27/2/2023-6/03/2023 | 6/3/2023-8/3/2023 | 8/3/2023-15/3/2023 | 15/3/2023-22/3/2023 | 22/3/2023-23/3/2023 | 23/3/2023-13/4/2023 | 28//3/2023-31/3/2023 | first Quarter
Date: Actual
Cost :Plan | [7 empty] | 70000 |  |  | 50000 |  |  | 120000 |  |  |  |  | 50000
Cost: Actual
Responsibility | [7 empty] | Procurement Officer | D.G Due Process |  | Procurement Officer | Procurement Officer | Procurement Officer | Procurement Officer | Ag. MD | D.G Due Process | Executive Governor | Ag. MD | Director Technical Support | Commissioner of Finance
Date: Plan | iv. Reinforcement/improvement of reticulation for 5km in 5No. Small towns | 020406/02 | STOWA/2022/CP/7 | NA | 5million | 2.5 million | Nominative Method | 31/01/2023-3/02/2023 | 6/02/2023-13/02/2023 | NA | 13/02/2023-17/2/2023 | 20/2/2023-27/2/2023 | 20/2/2023-27/2/2023 | 27/2/2023-6/03/2023 | 6/3/2023-8/3/2023 | 8/3/2023-15/3/2023 | 15/3/2023-22/3/2023 | 22/3/2023-23/3/2023 | 23/3/2023-13/4/2023 | 28//3/2023-31/3/2023 | First Quarter
Date: Actual
Cost: Plan | [7 empty] | 50000 |  |  | 50000 | [7 empty] | 20000
Cost : Actual
Responsibility | [7 empty] | Procurement Officer | D.G Due Process |  | Procurement Officer | Procurement Officer | Procurement Officer | Procurement Officer | Ag. MD | D.G Due Process | Executive Governor | Ag. MD | Director Technical Support | Commissioner of Finance
Date: Plan | v. Drilling of 2No. Additional Bore holes | 020406/02 | STOWA/2022/CP/8 | NA | 5million | 5 million | Nominative Method | 31/01/2023-3/02/2023 | 6/02/2023-13/02/2023 | NA | 13/02/2023-17/2/2023 | 20/2/2023-27/2/2023 | 20/2/2023-27/2/2023 | 27/2/2023-6/03/2023 | 6/3/2023-8/3/2023 | 8/3/2023-15/3/2023 | 15/3/2023-22/3/2023 | 22/3/2023-23/3/2023 | 23/3/2023-13/4/2023 | 28//3/2023-31/3/2023 | First Quarter
Date: Actual
Cost: Plan | [7 empty] | 50000 |  |  | 50000 | [7 empty] | 20000
Cost : Actual
Responsibility | [7 empty] | Procurement Officer | D.G Due Process |  | Procurement Officer | Procurement Officer | Procurement Officer | Procurement Officer | Ag. MD | D.G Due Process | Executive Governor | Ag. MD | Director Technical Support | Commissioner of Finance
Date: Plan | vi. Ongoing 2021 and 2022 constituency project | 020408/02 | STOWA/2022/CP/12 | NA | 380 million | 380 million | Open competitive Method | Ongoing project | ongoing project | Ongoing project | Ongoing project | Ongoing project | Ongoing project | Ongoing project | Ongoing project | Ongoing project | Ongoing project | Ongoing project | 23/3/2023-13/4/2023 | 28//3/2023-31/3/2023 | First Quarter
Date: Actual
Cost: Plan | [7 empty] | Ongoing project |  |  | ongoing project |  | ongoing project | [5 empty] | 20000
Cost : Actual
Responsibility | [7 empty] | Procurement Officer | D.G Due Process |  | Procurement Officer | Procurement Officer | Procurement Officer | Procurement Officer | Ag. MD | D.G Due Process | Executive Governor | Ag. MD | Director Technical Support | Commissioner of Finance
Date: Plan | vii. Procurement of 1No. (4WD) Hilux Motors vehicle | 020411/02 | STOWA/2022/CP/REHAB./1 | NA | 20million | 20million | Selective method | 3/4/2023-5/4/2023 | 6/4/2023-13/4/2023 | NA | 14/04/2023-19/4/2023 | 19/4/2023-24/4/2023 | 25//4/2023-28/4/2022 | 1/5/2023-5/5/2023 | 8/5/2023-15/5/2023 | 15/5/2023-22/5/2023 | 19/6/2023-23/6/2023 | 23/6/2022-27/6/2022 | 27/6/2023-5/7/2023 | 5/7/2023-12/7/2023 | second -quarter
Date: Actual
Cost :Plan | [7 empty] | 60000 |  |  | 80000 | [7 empty] | 50000
Cost: Actual
Responsibility | [7 empty] | Procurement Officer | D.G Due Process |  | Procurement Officer | Procurement Officer | Procurement Officer | Procurement Officer | Ag. MD | D.G. Due Procrss | Executive Governor | Ag. MD | Director Technical Support | Commissioner of Finance
Date: Plan | viii. Rehabilitation of existing small towns water supply schemes | 020404/02 | STOWA/2023/CP/REHAB./1 | NA | 400million | 100 million | Selective method | 3/4/2023-5/4/2023 | 6/4/2023-13/4/2023 | NA | 14/04/2023-19/4/2023 | 19/4/2023-24/4/2023 | 25//4/2023-28/4/2022 | 1/5/2023-5/5/2023 | 8/5/2023-15/5/2023 | 15/5/2023-22/5/2023 | 19/6/2023-23/6/2023 | 23/6/2022-27/6/2022 | 27/6/2023-5/7/2023 | 5/7/2023-12/7/2023 | second -quarter
Date: Actual
Cost :Plan | [18 empty] | 50000
Cost: Actual
Responsibility | [7 empty] | Procurement Officer | D.G Due Process |  | Procurement Officer | Procurement Officer | Procurement Officer | Procurement Officer | Ag. MD | D.G. Due Procrss | Executive Governor | Ag. MD | Director Technical Support | Commissioner of Finance
Date: Plan | ix. Reinforcement/improvement of reticulation for 5km in 5No. Small towns | 020406/02 | STOWA/2022/CP/7 | NA | 5million | 2.5 million | Nominative Method | 3/4/2023-5/4/2023 | 6/4/2023-13/4/2023 | NA | 14/04/2023-19/4/2023 | 19/4/2023-24/4/2023 | 25//4/2023-28/4/2022 | 1/5/2023-5/5/2023 | 8/5/2023-15/5/2023 | 15/5/2023-22/5/2023 | 19/6/2023-23/6/2023 | 23/6/2022-27/6/2022 | 27/6/2023-5/7/2023 | 5/7/2023-12/7/2023 | second -quarter
Date: Actual
Cost: Plan | [7 empty] | 50000 |  |  | 50000 | [7 empty] | 20000
Cost : Actual
Responsibility | [7 empty] | Procurement Officer | D.G Due Process |  | Procurement Officer | Procurement Officer | Procurement Officer | Procurement Officer | Ag. MD | D.G Due Process | Executive Governor | Ag. MD | Director Technical Support | Commissioner of Finance
Date: Plan | x. Purchase of office furnitures in the newly constructed conference Hall and Managing Director's office | 020404/02 | STOWA/2022/CP/5 | NA | 10 million | 10 millioin | Nominative Method | 3/4/2023-5/4/2023 | 6/4/2023-13/4/2023 | NA | 14/04/2023-19/4/2023 | 19/4/2023-24/4/2023 | 25//4/2023-28/4/2022 | 1/5/2023-5/5/2023 | 8/5/2023-15/5/2023 | 15/5/2023-22/5/2023 | 19/6/2023-23/6/2023 | 23/6/2022-27/6/2022 | 27/6/2023-5/7/2023 | 5/7/2023-12/7/2023 | second quarter
Date: Actual
Cost :Plan | [7 empty] | 50000 |  |  | 40000 | [7 empty] | 50000
Cost: Actual
Responsibility | [7 empty] | Procurement Officer | D.G Due Process |  | Procurement Officer | Procurement Officer | Procurement Officer | Procurement Officer | Ag. MD | D.G Due Process | Executive Governor | Ag. MD | Director Technical Support | Commissioner of Finance
Date: Plan | xi. Commencement of 2023 constituency projects | 020404/02 | STOWA/2023/CP/6 | NA | 681million | 681million | Open competitive Method | 3/4/2023-5/4/2023 | 6/4/2023-13/4/2023 | NA | 13/04/2023-25/5/2023 | 13/04/2023-25/5/2023 | 13/04/2023-25/5/2023 | 25/5/2023-8/6/2023 | 8/6/2023-13/6/2023 | 13/6/2023-20/6/2023 | 20/6/2023-23/6/2023 | 23/6/2023-26/6/2023 | 26/6/2023-24/7/2023 | 24/7/2023-31/7/2023 | second quarter
Date: Actual
Cost :Plan | [7 empty] | 50000 |  |  | 60000 | 700000 | [6 empty] | 50000
Cost: Actual
Responsibility | [7 empty] | Procurement Officer | D.G Due Process |  | Procurement Officer | Procurement Officer | Procurement Officer | Procurement Officer | Ag. MD | D.G Due Process | Executive Governor | Ag. MD | Director Technical Support | Commissioner of Finance
Date: Plan | xii. Construction of 30No. New conventional solar water schemes across the 7 zones | 020408/02 | STOWA/2022/CP/2 | NA | 224.24 million | 48.08 million | sellective method | 3/4/2023-5/4/2023 | 6/4/2023-13/4/2023 | NA | 14/04/2023-19/4/2023 | 19/4/2023-24/4/2023 | 25//4/2023-28/4/2022 | 1/5/2023-5/5/2023 | 8/5/2023-15/5/2023 | 15/5/2023-22/5/2023 | 19/6/2023-23/6/2023 | 23/6/2022-27/6/2022 | 27/6/2023-5/7/2023 | 5/7/2023-12/7/2023 | second quarter
Date: Actual
Cost :Plan | [7 empty] | 20000 |  |  | 30000 |  |  | 120000 | 30000 |  |  |  | 50000
Cost: Actual
Responsibility | [7 empty] | Procurement Officer | D.G Due Process |  | Procurement Officer | Procurement Officer | Procurement Officer | Procurement Officer | Ag. MD | D.G. Due Procrss | Executive Governor | Ag. MD | Director Technical Support | Commissioner of Finance
Date: Plan | xiii.Conversion and upgrading of 36No. motorized water supply scheme to solar powered water supply schemes | 020408/02 | STOWA/2023/PROJ/CP/6 | NA | 500 Million | 100 Million | selective competitive Method | 3/4/2023-5/4/2023 | 6/4/2023-13/4/2023 | NA | 14/04/2023-19/4/2023 | 19/4/2023-24/4/2023 | 25//4/2023-28/4/2022 | 1/5/2023-5/5/2023 | 8/5/2023-15/5/2023 | 15/5/2023-22/5/2023 | 19/6/2023-23/6/2023 | 23/6/2022-27/6/2022 | 27/6/2023-5/7/2023 | 5/7/2023-12/7/2023 | second quarter
Date: Actual
Cost :Plan | [7 empty] | 70000 |  |  | 50000 |  |  | 120000 |  |  |  |  | 50000
Cost: Actual
Responsibility | [7 empty] | Procurement Officer | D.G Due Process |  | Procurement Officer | Procurement Officer | Procurement Officer | Procurement Officer | Ag. MD | D.G Due Process | Executive Governor | Ag. MD | Director Technical Support | Commissioner of Finance
Date: Plan | xiv. Ongoing 2021 and 2022 constituency project | 020408/02 | STOWA/2022/CP/12 | NA | 380 million | 380 million | Open competitive Method | Ongoing project | ongoing project | Ongoing project | Ongoing project | Ongoing project | Ongoing project | Ongoing project | Ongoing project | Ongoing project | Ongoing project | Ongoing project | 27/6/2023-5/7/2023 | 5/7/2023-12/7/2023 | second -quarter
Date: Actual
Cost: Plan | [7 empty] | Ongoing project |  |  | ongoing project |  | ongoing project | [5 empty] | 20000
Cost : Actual
Responsibility | [7 empty] | Procurement Officer | D.G Due Process |  | Procurement Officer | Procurement Officer | Procurement Officer | Procurement Officer | Ag. MD | D.G Due Process | Executive Governor | Ag. MD | Director Technical Support | Commissioner of Finance
Date: Plan | xv. Purchase of 32No. Motor cycles to District officers/commercial officersacross the 7 zones and Headquarter | 020411/02 | STOWA/2022/PRCMNT/2 | NA | 20million | 20million | selective competitive Method | 3/7/2023-7/7/2023 | 7/7/2023-14/7/2023 | NA | 14/7/2023-21/7/2023 | 21/7/2023-28/7/2023 | 21/7/2023-28/7/2023 | 28/7/2023-4/8/2023 | 4/8/2023-11/8/2023 | 11/8/2023-18/8/2023 | 18/8/2023-25/8/20223 | 25/8/2023-29/8/2023 | 29/8/2023-18/9/2023 | 18/9/2023-25/9/2023 | Third Quarter
Date: Actual
Cost :Plan | [7 empty] | 30000 |  |  | 50000 | [7 empty] | 150000
Cost: Actual
Responsibility | [7 empty] | Procurement Officer | D.G Due Process |  | Procurement Officer | Procurement Officer | Procurement Officer | Procurement Officer | Ag. MD | D.G Due Process | Executive Governor | Ag. MD | Director Technical Support | Commissioner of Finance
Date: Plan | xvi. Rehabilitation of existing small towns water supply schemes | 020404/02 | STOWA/2023/CP/REHAB./1 | NA | 400million | 100 million | Selective method | 3/7/2023-7/7/2023 | 7/7/2023-14/7/2023 | NA | 14/7/2023-21/7/2023 | 21/7/2023-28/7/2023 | 21/7/2023-28/7/2023 | 28/7/2023-4/8/2023 | 8/5/2023-15/5/2023 | 11/8/2023-18/8/2023 | 18/8/2023-25/8/20223 | 25/8/2023-29/8/2023 | 29/8/2023-18/9/2023 | 18/9/2023-25/9/2023 | Third Quarter
Date: Actual
Cost :Plan | [18 empty] | 50000
Cost: Actual
Responsibility | [7 empty] | Procurement Officer | D.G Due Process |  | Procurement Officer | Procurement Officer | Procurement Officer | Procurement Officer | Ag. MD | D.G. Due Procrss | Executive Governor | Ag. MD | Director Technical Support | Commissioner of Finance
Date: Plan | xvii.Conversion and upgrading of 36No. motorized water supply scheme to solar powered water supply schemes | 020408/02 | STOWA/2023/PROJ/CP/6 | NA | 500 Million | 100 Million | selective competitive Method | 3/7/2023-7/7/2023 | 7/7/2023-14/7/2023 | NA | 14/7/2023-21/7/2023 | 21/7/2023-28/7/2023 | 21/7/2023-28/7/2023 | 28/7/2023-4/8/2023 | 8/5/2023-15/5/2023 | 11/8/2023-18/8/2023 | 18/8/2023-25/8/20223 | 25/8/2023-29/8/2023 | 29/8/2023-18/9/2023 | 18/9/2023-25/9/2023 | Third Quarter
Date: Actual
Cost :Plan | [7 empty] | 70000 |  |  | 50000 |  |  | 120000 |  |  |  |  | 50000
Cost: Actual
Responsibility | [7 empty] | Procurement Officer | D.G Due Process |  | Procurement Officer | Procurement Officer | Procurement Officer | Procurement Officer | Ag. MD | D.G Due Process | Executive Governor | Ag. MD | Director Technical Support | Commissioner of Finance
Date: Plan | xviii. Construction of 30No. New conventional solar water schemes across the 7 zones | 020408/02 | STOWA/2022/CP/2 | NA | 224.24 million | 48.08 million | sellective method | 3/7/2023-7/7/2023 | 7/7/2023-14/7/2023 | NA | 14/7/2023-21/7/2023 | 21/7/2023-28/7/2023 | 21/7/2023-28/7/2023 | 28/7/2023-4/8/2023 | 8/5/2023-15/5/2023 | 11/8/2023-18/8/2023 | 18/8/2023-25/8/20223 | 25/8/2023-29/8/2023 | 29/8/2023-18/9/2023 | 18/9/2023-25/9/2023 | Third Quarter
Date: Actual
Cost :Plan | [7 empty] | 20000 |  |  | 30000 |  |  | 120000 | 30000 |  |  |  | 50000
Cost: Actual
Responsibility | [7 empty] | Procurement Officer | D.G Due Process |  | Procurement Officer | Procurement Officer | Procurement Officer | Procurement Officer | Ag. MD | D.G. Due Procrss | Executive Governor | Ag. MD | Director Technical Support | Commissioner of Finance
Date: Plan | xix. Construction of public convenience at small towns | 020404/02 | STOWA/2022/PROJ/CP/6 | NA | 3 million | 3million | Nominative Method | 3/7/2023-7/7/2023 | 7/7/2023-14/7/2023 | NA | 14/7/2023-21/7/2023 | 21/7/2023-28/7/2023 | 21/7/2023-28/7/2023 | 28/7/2023-4/8/2023 | 8/5/2023-15/5/2023 | 11/8/2023-18/8/2023 | 18/8/2023-25/8/20223 | 25/8/2023-29/8/2023 | 29/8/2023-18/9/2023 | 18/9/2023-25/9/2023 | Third Quarter
Date: Actual
Cost :Plan | [7 empty] | 30000 |  |  | 50000 | [7 empty] | 30000
Cost: Actual
Responsibility | [7 empty] | Procurement Officer | D.G Due Process |  | Procurement Officer | Procurement Officer | Procurement Officer | Procurement Officer | Ag. MD | D.G Due Process | Executive Governor | Ag. MD | Director Technical Support | Commissioner of Finance
Date: Plan | xxi. Rehabilitation of existing small towns water supply schemes | 020404/02 | STOWA/2023/CP/REHAB./1 | NA | 400million | 100 million | Selective method | 3/10/2023-6/10/2023 | 6/10/2023-13/10/2023 | NA | 13/10/2023-20/10/2023 | 20/10/2023-31/10/2023 | 20/10/2023-31/10/2023 | 31/10/2023-7/11/2023 | 7/11/2023-8/11/2023 | 8/11/2023-15/11/2023 | 15/11/2023-22/11/2023 | 22/11/2023-23/11/2023 | 23/11/2023-21/12/2023 | 21/12/2023-29/12/2023 | Fourth Quarter
Date: Actual
Cost :Plan | [18 empty] | 50000
Cost: Actual
Responsibility | [7 empty] | Procurement Officer | D.G Due Process |  | Procurement Officer | Procurement Officer | Procurement Officer | Procurement Officer | Ag. MD | D.G. Due Procrss | Executive Governor | Ag. MD | Director Technical Support | Commissioner of Finance
Date: Plan | xxii. Ongoing 2020 and 2021 constituency project | 020408/02 | STOWA/2022/PROJ/CP/10 | NA | 380million | 380million | Open commpetitive Method | Ongoing project | ongoing project | NA | Ongoing project | Ongoing project | ongoing project | ongoing project | Ongoing project | Ongoing project | Ongoing project | Ongoing project | 23/11/2023-21/12/2023 | 21/12/2023-29/12/2023 | Fourth Quarter
Date: Actual
Cost :Plan | [7 empty] | Ongoing project | [10 empty] | 30000
Cost: Actual
Responsibility | [7 empty] | Procurement Officer | D.G Due Process |  | Procurement Officer | Procurement Officer | Procurement Officer | Procurement Officer | Ag. MD | D.G Due Process | Executive Governor | Ag. MD | Director Technical Support | Commissioner of Finance
Date: Plan | xxiii.Conversion and upgrading of 36No. motorized water supply scheme to solar powered water supply schemes | 020408/02 | STOWA/2023/PROJ/CP/6 | NA | 500 Million | 100 Million | selective competitive Method | 3/10/2023-6/10/2023 | 6/10/2023-13/10/2023 | NA | 13/10/2023-20/10/2023 | 20/10/2023-31/10/2023 | 20/10/2023-31/10/2023 | 31/10/2023-7/11/2023 | 7/11/2023-8/11/2023 | 8/11/2023-15/11/2023 | 15/11/2023-22/11/2023 | 22/11/2023-23/11/2023 | 23/11/2023-21/12/2023 | 21/12/2023-29/12/2023 | Fourth Quarter
Date: Actual
Cost :Plan | [7 empty] | 70000 |  |  | 50000 |  |  | 120000 |  |  |  |  | 50000
Cost: Actual
Responsibility | [7 empty] | Procurement Officer | D.G Due Process |  | Procurement Officer | Procurement Officer | Procurement Officer | Procurement Officer | Ag. MD | D.G Due Process | Executive Governor | Ag. MD | Director Technical Support | Commissioner of Finance
Date: Plan | xxiv.Establishment of WCAs in communities, involving community engagement,sensitization,registration, training and follow up visit to 190 communities for monitoring activities | 020411/02 | STOWA/2022/WCA/11 | NA | 2million | 2million | Direct | 3/10/2023-6/10/2023 |  | NA | Direct | Direct | Direct | Direct | Direct | Direct | 10/11/2023-17/11/2023 | Direct | Direct | 17/11/2023-21/11/2023 | Fourth Quarter
Date: Actual
Cost :Plan
Cost: Actual
Responsibility | [7 empty] | Director Community Mobilization | D.G Due Process |  | Procurement Officer | Procurement Officer | Procurement Officer | Procurement Officer | Ag. MD | D.G Due Process | Executive Governor | Ag. MD | Director Technical Support | Commissioner of Finance
Date: Plan | xxv. Capacity building of Technical Personnel on solar based installation and maintenance | 020411/02 | STOWA/2022/SEMINAR/14 | NA | 2million | 2million | Direct | 3/10/2023-6/10/2023 | Direct | NA | Direct | Direct | Direct | Direct | Direct | Direct | 10/11/2023-17/11/2023 | Direct | Direct | 17/11/2023-21/11/2023 | Fourth Quarter
Date: Actual
Cost :Plan
Cost: Actual
Responsibility | [7 empty] | Director Community Mobilization | [6 empty] | Ag. MD |  | Executive Governor | Ag. MD | Director Technical Support | Commissioner of Finance
Date: Plan | xxvi. Community mobilization and sesitization on open Defication at small towns | 020412/02 | STOWA/2022/SENSITIZATION/15 | NA | 2million | 2million | Direct | 3/10/2023-6/10/2023 | Direct | NA | Direct | Direct | Direct | Direct | Direct | Direct | 10/11/2023-17/11/2023 | Direct | Direct | 17/11/2023-21/11/2023 | Fourth Quarter
Date: Actual
Cost :Plan
Cost: Actual
Responsibility | [7 empty] | Director Community Mobilization | [6 empty] | Ag. MD |  | Executive Governor | Ag. MD | Director Technical Support | Commissioner of Finance

## CS
PROCUREMENT PLAN FOR CONSULTING SERVICES.
MINISTRY/ AGENCY:
BUDGET YEAR:
Project Description | Package Number | CONTRACT TYPE |  |  |  | PREPARATION OF PROPOSALS |  |  |  | SHORTLIST |  | CONSULTANT PROPOSAL |  | PROPOSAL EVALUATION AND NEGOTIATION | [5 empty] | CONTRACT FINALIZATION |  |  | CONTRACT IMPLEMENTATION
|  | Lumpsum or Time-Based | Budgetary Amount in Naira | Plan Vs Actual | Approval Threshhold | Preparation and Submission by MDAs | MDA Approval/ LASPPA 'Certificate of Compliance" | Advertisement | Lead-Time Beforte Shortlist | Submission Date | MDA Approval/ LASPPA 'Certificate of Compliance" | Invitation Date | Submission / Opening Date | Submission Evaluation Report (T) | MDA Approval/ LASPPA 'Certificate of Compliance" | Opening/ Evaluation of Financial Proposals | Submission Evaluation Report (T) (F) | Negotiation (if any) | Certificate of Clearance Date | Contract Amount in Naira | Contract Offer | Contract Signature | Mobilization Advance Payment | Draft Report | Final Report | Final Cost | Action Party | Champion